Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 12 October 2026 |
| --- | --- |
| Team ID | SWUID2026403111 |
| Project Name | IMovies - Online Movie, Event & Entertainment Ticket Booking System |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule, and Estimation (4 Marks)

Product Backlog & Sprint Schedule

| Sprint | Functional Requirement (Epic) | User Story Number | User Story / Task | Story Points | Priority | Team Members |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | Project Setup & Location | USN-1 | As a developer, I can set up the Spring Boot + React project, database migrations and CI pipeline (NFR-MNT-001/002). | 8 | High |  |
|  |  | USN-2 | As a user, I can select or detect my city and change it later (FR-LOC-001 to 006). | 3 | High |  |
|  | User Authentication & Profile | USN-3 | As a user, I can register with name, email, mobile and password and verify with OTP (FR-AUTH-001 to 003). | 5 | High |  |
|  |  | USN-4 | As a user, I can log in/out securely with JWT and role-based access (FR-AUTH-004, 007, 010). | 5 | High |  |
|  |  | USN-5 | As a user, I can reset my password through a time-limited link/OTP (FR-AUTH-006). | 3 | Medium |  |
|  |  | USN-6 | As a user, I can edit my profile, change my password and upload a photo (FR-USR-001, 003, 004). | 3 | Medium |  |
| Sprint-2 | Movie & Cinema Catalogue | USN-7 | As an admin, I can add, edit and publish movies with poster, cast and trailer (FR-ADM-002, FR-MOV-001). | 5 | High |  |
|  |  | USN-8 | As an admin, I can manage cinemas, screens and seat layouts (FR-CIN-001/003, FR-SCR-001 to 004). | 8 | High |  |
|  |  | USN-9 | As a user, I can see Now Showing, Coming Soon and Trending movies on the home page (FR-MOV-002, 005, 006). | 5 | High |  |
|  |  | USN-10 | As a user, I can open a movie page with trailer, cast, reviews and Book Tickets (FR-MOV-003, 004). | 3 | High |  |
|  | Search & Discovery | USN-11 | As a user, I can search movies, cinemas and events with auto-complete suggestions (FR-SRCH-001, 002, 004). | 5 | High |  |
|  |  | USN-12 | As a user, I can filter by language, genre, format, certification and sort results (FR-SRCH-005, 006). | 3 | Medium |  |
| Sprint-3 | Shows & Seat Selection | USN-13 | As a cinema manager, I can create, edit and cancel shows with overlap checking (FR-SHW-001 to 005). | 5 | High |  |
|  |  | USN-14 | As a user, I can view cinemas, dates and showtimes for a movie (FR-SHW-001, FR-CIN-002). | 3 | High |  |
|  |  | USN-15 | As a user, I can pick seats on an interactive seat map with live availability (FR-SEAT-001 to 004). | 8 | High |  |
|  |  | USN-16 | As a user, I can lock selected seats for 10 minutes with a countdown timer (FR-SEAT-005 to 008). | 8 | High |  |
|  |  | USN-17 | As a system, I release expired locks automatically through a scheduler (FR-SEAT-007, BR-003). | 3 | High |  |
|  |  | USN-18 | As a user, I can view a cinema page with amenities, movies and prices (FR-CIN-002). | 3 | Medium |  |
| Sprint-4 | Booking, Payment & Tickets | USN-19 | As a user, I can see an order summary with fees, taxes and totals (FR-BOOK-003, 005). | 5 | High |  |
|  |  | USN-20 | As a user, I can add food and beverages to my booking (FR-FNB-001 to 003). | 5 | Medium |  |
|  |  | USN-21 | As a user, I can apply a valid coupon code at checkout (FR-CPN-001 to 004). | 5 | Medium |  |
|  |  | USN-22 | As a user, I can pay through the mock gateway and see success or failure (FR-PAY-001 to 006). | 8 | High |  |
|  |  | USN-23 | As a user, I receive a confirmation with QR ticket I can download as PDF (FR-TKT-001 to 003). | 5 | High |  |
|  |  | USN-24 | As a user, I can view upcoming and past bookings in My Bookings (FR-BOOK-008). | 3 | High |  |
| Sprint-5 | Cancellation & Refunds | USN-25 | As a user, I can cancel a booking up to 30 minutes before the show and see my refund (FR-CAN-001 to 006, 008). | 8 | High |  |
|  |  | USN-26 | As an admin, I can process refunds, and shows cancelled by a cinema auto-refund 100% (FR-CAN-007, 009). | 5 | Medium |  |
|  | Events Module | USN-27 | As an organizer, I can create events with ticket types, prices and capacity (FR-EVT-002, 003, 008). | 5 | High |  |
|  |  | USN-28 | As a user, I can browse events and book tickets by category and quantity (FR-EVT-001, 004, 005, 007). | 8 | High |  |
|  | Notifications | USN-29 | As a user, I receive in-app and email notifications for bookings, cancellations and refunds (FR-NTF-001 to 003). | 5 | Medium |  |
| Sprint-6 | Engagement & Recommendations | USN-30 | As a user, I can rate and review movies, events and cinemas (FR-REV-001 to 004). | 3 | Medium |  |
|  |  | USN-31 | As a user, I can save movies, events and cinemas to favorites (FR-FAV-001). | 2 | Low |  |
|  |  | USN-32 | As a user, I see recommended movies based on my history and preferences (FR-REC-001, 002). | 3 | Low |  |
|  | Admin, Analytics & Release | USN-33 | As an admin, I can view the dashboard KPIs and revenue, booking and occupancy charts (FR-ADM-001, FR-ANL-001 to 004). | 5 | Medium |  |
|  |  | USN-34 | As an admin, I can manage users, bookings, coupons and banners (FR-ADM-004 to 006). | 5 | Medium |  |
|  |  | USN-35 | As cinema staff, I can verify a ticket by scanning its QR code (FR-TKT-004, 005). | 3 | Medium |  |
|  |  | USN-36 | As a team, we complete security, performance and E2E testing and deploy the system (Sections 15-17). | 8 | High |  |

Project Tracker, Velocity & Burndown Chart

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date (Planned) | Story Points Completed (as on Planned End Date) | Sprint Release Date (Actual) |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint-1 | 27 | 14 Days | 19 Oct 2026 | 1 Nov 2026 |  |  |
| Sprint-2 | 29 | 14 Days | 2 Nov 2026 | 15 Nov 2026 |  |  |
| Sprint-3 | 30 | 14 Days | 16 Nov 2026 | 29 Nov 2026 |  |  |
| Sprint-4 | 31 | 14 Days | 30 Nov 2026 | 13 Dec 2026 |  |  |
| Sprint-5 | 31 | 14 Days | 14 Dec 2026 | 27 Dec 2026 |  |  |
| Sprint-6 | 29 | 14 Days | 28 Dec 2026 | 10 Jan 2027 |  |  |
| Total | 177 | 84 Days | 19 Oct 2026 | 10 Jan 2027 |  |  |

Velocity

Total story points: 177 across 6 sprints of 14 days (84 days). Average velocity = 177 / 6 = 29.5 story points per sprint (about 2.11 points per day).

Priority key: High = must-have for the booking flow; Medium = should-have; Low = could-have. Story points use a 1-8 scale. Actual completion and release dates are filled in as each sprint closes.

Burndown Chart